## By Project
PO Number | Location | Name | Project Code | Project | PM | Billing rate | Projected Effort (Aug) | Projected Effort (Sep) 20 Days 04/09 to 02/10 | Projected Effort (Oct) 20 Days 02/10 to 30/10 03/10 - PH AU 10/10 - PH IN | Projected Amt (Aug) | Projected Amt (Sep) | Projected Amt (Oct) | Comments | Period | Billing Hrs | Rate/Hr | Sep Status | Oct Status
1001 | Onshore | Priyam Gaur | H.3244 | DM Blue Martini Replatform & DR Solution | Evelyn | 864 | 0 | 0 | 10 | 0 | 0 | 8640 |  | 1 Aug to 31 oct | 80 | 108 |  | PO received
1001 | Onshore | Vinod Kumar | H.3244 | DM Blue Martini Replatform & DR Solution | Evelyn | 864 | 13 | 17 | 18 | 11232 | 14688 | 15552 | Training 08/09 - 09/09 Leave - 19/09 Sick Leave - 21/10 | 1 Aug to 31 oct | 144 | 108 | Invoice Generated
1001 | Onshore | Goms | H.3244 | DM Blue Martini Replatform & DR Solution | Evelyn | 634 | 0 | 20 | 0 | 0 | 12680 | 0 |  | 1 Aug to 31 oct | 0 | 79.25
1003 | Offshore | Amey Vaidya | H.3244 | DM Blue Martini Replatform & DR Solution | Evelyn | 298 | 0 | 19 | 19 | 0 | 5662 | 5662 | Sick - 9/09 | 1 Aug to 31 oct | 152 | 37.25
1001 | Onshore | Sumit Poddar | H.3244 | DM Blue Martini Replatform & DR Solution | Evelyn | 634 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 Aug to 31 oct | 0 | 79.25
1002 | Onshore | Tej | H.3244 | DM Blue Martini Replatform & DR Solution | Evelyn | 634 | 0 | 0 | 19 | 0 | 0 | 12046 |  | 1 Aug to 31 oct | 152 | 79.25
[10 empty] | 11232 | 33030 | 41900
2001 | Onshore | Ayush P | H.3201 | DM Enhancements FY17 | Tasanee | 634 | 14 | 17 | 18 | 8876 | 10778 | 11412 | Leave 14 days - 18/08 to 25/08, 29/08 - 2/09, 05/09- 07/09 | 1 Aug to 31 oct | 144 | 79.25 | Invoice Generated | PO Pending
2001 | Onshore | Priyam Gaur | H.3201 | DM Enhancements FY17 | Tasanee | 864 | 25 | 18 | 9 | 21600 | 15552 | 7776 | Training 05/09 - 06/09 | 1 Aug to 31 oct | 72 | 108
2001 | Onshore | Francis | H.3201 | DM Enhancements FY17 | Tasanee | 720 | 1 | 1 | 1 | 720 | 720 | 720 |  | 1 Aug to 31 oct | 8 | 90
2002 | Onshore | VAB Naseerudeen | H.3201 | DM Enhancements FY17 | Tasanee | 792 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 Aug to 31 oct | 0 | 99
2003 | Onshore | Sivaranjani | H.3201 | DM Enhancements FY17 | Tasanee | 634 | 24 | 5 | 19 | 15216 | 3170 | 12046 | Sick 2/08, Leave 15 days - 05/09 to 23/09 | 1 Aug to 31 oct | 152 | 79.25
2003 | Onshore | Goms | H.3201 | DM Enhancements FY17 | Tasanee | 634 | 25 | 0 | 17 | 15850 | 0 | 10778 | Sick leave- 11/10 , 17/10 | 1 Aug to 31 oct | 136 | 79.25
2004 | Offshore | Vanisri | H.3201 | DM Enhancements FY17 | Tasanee | 278 | 22 | 19 | 12 | 6116 | 5282 | 3336 | Leave - 15/08, Sick 25-26/08, 3-7/10, 11/10, 12/10 | 1 Aug to 31 oct | 96 | 34.75
2002 | Onshore | Sumit Poddar | H.3201 | DM Enhancements FY17 | Tasanee | 634 | 0 | 0 | 17 | 0 | 0 | 10778 | Sick 6-7/10 | 1 Aug to 31 oct | 136 | 79.25
[10 empty] | 68378 | 35502 | 56846
3001 | Onshore | Vinod Kumar | H.3100 | SOH & Availability Management | Evelyn | 864 | 12 | 0 | 0 | 10368 | 0 | 0 |  | 1 Aug to 31 oct | 0 | 108 | Invoice Generated | Closed
3001 | Onshore | VAB Naseerudeen | H.3100 | SOH & Availability Management | Evelyn | 792 | 24 | 0 | 0 | 19008 | 0 | 0 | 11/08 Sick Leave | 1 Aug to 31 oct | 0 | 99
3001 | Onshore | Francis | H.3100 | SOH & Availability Management | Evelyn | 720 | 1 | 1 | 0 | 720 | 720 | 0 |  | 1 Aug to 31 oct | 0 | 90
3001 | Onshore | Tej | H.3100 | SOH & Availability Management | Evelyn | 634 | 24 | 19 | 0 | 15216 | 12046 | 0 | 16/08 & 23/09 - Sick Leave | 1 Aug to 31 oct | 0 | 79.25
3001 | Onshore | Sumit Poddar | H.3100 | SOH & Availability Management | Evelyn | 634 | 25 | 19 | 0 | 15850 | 12046 | 0 | Sick - 12/09 |  | 0 | 79.25
3002 | Offshore | Amey Vaidya | H.3100 | SOH & Availability Management | Evelyn | 298 | 21 | 0 | 0 | 6258 | 0 | 0 | Leave - 04/08, 05/08, 25/08 15/08- Public Holiday | 1 Aug to 31 oct | 0 | 37.25
[10 empty] | 67420 | 24812 | 0
4001 | Onshore | VAB Naseerudeen | H.3160 | DM QAS Address Validation | Tasanee | 792 | 0 | 19 | 18 | 0 | 15048 | 14256 | Leave - 12/09 Sick - 19/10 | 1 Aug to 31 oct | 144 | 99 | Invoice Generated | PO received
[10 empty] | 0 | 15048 | 14256
Note on L4: Created separate PO #4400718617 under Enhancements -Evelyn Manaid

## Sheet1
Location | Name | Project | PM | Billing rate | Projected Effort (Aug) | Projected Effort (Sep) 20 Days 04/09 to 02/10 | Projected Effort (Oct) 20 Days 02/10 to 30/10 03/10 - PH AU 10/10 - PH IN | Projected Amt (Aug) | Projected Amt (Sep) | Projected Amt (Oct) | Comments | Period | Billing Hrs | Rate/Hr
Onshore | Ayush P | H.3201 DM Enhancements FY17 | Tasanee | 634 | 14 | 17 | 19 | 8876 | 10778 | 12046 | Leave 14 days - 18/08 to 25/08, 29/08 - 2/09, 05/09- 07/09 | 1 Aug to 31 oct | 112 | 79.25
Onsite | Priyam Gaur | H.3201 DM Enhancements FY17 | Tasanee | 864 | 25 | 18 | 19 | 21600 | 15552 | 16416 | Training 05/09 - 06/09 | 1 Aug to 31 oct | 200 | 108
Onsite | Francis | H.3201 DM Enhancements FY17 | Tasanee | 720 | 1 | 1 | 1 | 720 | 720 | 720 |  | 1 Aug to 31 oct | 8 | 90
Onsite | Vinod Kumar | H.XXXX DM Product Lifecycle | Tasanee | 864 | 13 | 17 | 19 | 11232 | 14688 | 16416 | Training 08/09 - 09/09 Leave - 19/09 | 1 Aug to 31 oct | 104 | 108
Onshore | VAB Naseerudeen | H.3201 DM Enhancements FY17 | Tasanee | 792 | 0 | 0 | 19 | 0 | 0 | 15048 |  | 1 Aug to 31 oct | 0 | 99
Onsite | Sivaranjani | H.3201 DM Enhancements FY17 | Tasanee | 634 | 24 | 5 | 19 | 15216 | 3170 | 12046 | Sick 2/08, Leave 15 days - 05/09 to 23/09 | 1 Aug to 31 oct | 192 | 79.25
Onsite | Tej | H.3201 DM Enhancements FY17 | Tasanee | 634 | 0 | 0 | 19 | 0 | 0 | 12046 |  | 1 Aug to 31 oct | 0 | 79.25
Onsite | Goms | H.3201 DM Enhancements FY17 | Tasanee | 634 | 25 | 0 | 0 | 15850 | 0 | 0 |  | 1 Aug to 31 oct | 200 | 79.25
Onsite | Goms | H.XXXX DM Product Lifecycle | Tasanee | 634 | 0 | 20 | 19 | 0 | 12680 | 12046 |  | 1 Aug to 31 oct | 0 | 79.25
Offshore | Vanisri | H.3201 DM Enhancements FY17 | Tasanee | 278 | 22 | 19 | 20 | 6116 | 5282 | 5560 | Leave - 15/08, Sick 25-26/08 | 1 Aug to 31 oct | 176 | 34.75
Offshore | Amey Vaidya | H.XXXX DM Product Lifecycle | Tasanee | 298 | 0 | 19 | 20 | 0 | 5662 | 5960 | Sick - 9/09 | 1 Aug to 31 oct | 0 | 37.25
Onsite | Sumit Poddar | H.3201 DM Enhancements FY17 | Tasanee | 634 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 Aug to 31 oct | 0 | 79.25
Onsite | Sumit Poddar | H.XXXX DM Product Lifecycle | Tasanee | 634 | 0 | 19 | 19 | 0 | 12046 | 12046 | Sick - 12/09 | 1 Aug to 31 oct | 0 | 79.25
[8 empty] | 79610 | 80578 | 120350 |  |  | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
Onsite | Vinod Kumar | H.3100 SOH & Availability Management | Evelyn | 864 | 12 | 0 | 0 | 10368 | 0 | 0 |  | 1 Aug to 31 oct | 96 | 108
Onshore | VAB Naseerudeen | H.3100 SOH & Availability Management | Evelyn | 792 | 24 | 19 | 0 | 19008 | 15048 | 0 | 11/08 Sick Leave; Leave - 12/09 | 1 Aug to 31 oct | 192 | 99
Onshore | Francis | H.3100 SOH & Availability Management | Evelyn | 720 | 1 | 1 | 1 | 720 | 720 | 720 |  | 1 Aug to 31 oct | 8 | 90
Onsite | Tej | H.3100 SOH & Availability Management | Evelyn | 634 | 24 | 20 | 0 | 15216 | 12680 | 0 | 16/08 Sick Leave | 1 Aug to 31 oct | 192 | 79.25
Onsite | Sumit Poddar | H.3100 SOH & Availability Management | Evelyn | 634 | 25 | 0 | 0 | 15850 |  |  |  |  | 200 | 79.25
Offshore | Amey Vaidya | H.3100 SOH & Availability Management | Evelyn | 298 | 21 | 0 | 0 | 6258 | 0 | 0 | Leave - 04/08, 05/08, 25/08 15/08- Public Holiday | 1 Aug to 31 oct | 168 | 37.25
[8 empty] | 67420 | 28448 | 720